## Migration Status
Product Name/ Inventory | Regional Owner | Strategic | Priority | Comments/Status | GitHub Migration | GitHub Actions | JIRA Migration | overall_migration_status | migration_completion_score
C4H | Italy | YES | 1 | GitHub Migration: The code repository is migrated and deployed successfully. GitHub Actions Integration: The build pipeline is being transitioned to GitHub Actions, since it is an optional activity, the team chose not to deploy it on the dev environment. As of July 29, 2025, they have shown interest in adopting GitHub Actions, and an analysis is in progress Corporate JIRA Migration: Migration to corporate JIRA is completed. | Yes | Not Applicable | Yes | Mostly Migrated | 67
Clinalytix | PE&T | YES | 1 | GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: In progress by Dev. Team Corporate JIRA Migration: In porgress, planned timeline is yet to finalized | Yes | Commencing | Commencing | Partially Migrated | 33
Orbis | PE&T | YES | 1 | GitHub Migration: The code repositories previously hosted on Bitbucket and GitLab have been successfully migrated to GitHub by product team. Migration of rest repositories, such as SVN and others, has not yet commenced. GitHub Actions Integration: Integration will occur as needed since it is optional. Corporate JIRA Migration: Already moved to JIRA corporate | Partially Completed | As Needed | Yes | Partially Migrated | 34
GARSIA | Italy | YES | 1 | GitHub Migration: The code repository is migrated and deployed successfully. GitHub Actions Integration: The build pipeline is being transitioned to GitHub Actions, since it is an optional activity, the team chose not to deploy it on the dev environment. Corporate JIRA Migration: Migration to corporate JIRA is completed. | Yes | Not Applicable | Yes | Mostly Migrated | 67
ORBIS U/ORBIS U RIS | PE&T | YES | 1 | Since it's part of ORBIS, it will be handled during the ORBIS repository migration. | Partially Completed | As Needed | Yes | Migration Pending | 0
Info4U | PE&T | YES | 1 | Since it's part of ORBIS, it will be handled during the ORBIS repository migration. | Partially Completed | As Needed | Yes | Migration Pending | 0
Patient XCare Suite | PE&T | YES | 1 | Fully aligned with Tooling Landscape program's objective, confirmed by Stefan Grossmann on 13-Feb-2025 GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes | Fully Migrated | 100
ORBIS ERP | PE&T | YES | 1 | Since it's part of ORBIS, it will be handled during the ORBIS repository migration. | Partially Completed | As Needed | Yes | Migration Pending | 0
DeepUnity | DACH | YES | 1 | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes | Fully Migrated | 100
Dedalus Care PAS EMR | PE&T | YES | 1 | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: Team shows interest to continue with Jenkins instead of GitHub Actions Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Not Applicable | Yes | Mostly Migrated | 67
HERO | Italy | YES | 1 | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: Team shows interest to continue with Jenkins instead of GitHub Actions Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Not Applicable | Yes | Mostly Migrated | 67
4C Solution - C4C(aka P4C) | Italy | YES | 1 | Awaiting confirmation from Team | TBD | TBD | Yes | Migration Pending | 0
In Vitro LIS | Italy | YES | 1 | Mikhaël Sayegh will update after a workshop planned on beginning of July | TBD | TBD | Yes | Migration Pending | 0
4C Solution - O4C | Italy | YES | 1 | GitHub Migration: In progressGitHub. GitHub Actions Integration: Integration will occur as needed since it is optional. Corporate JIRA Migration: Already moved to JIRA corporate | TBD | TBD | Yes | Partially Migrated | 34
Global RIS | DACH | YES | 1 | Fully aligned with Tooling Landscape program's objective, confirmed by Michaela Lehner on 30th Apr 2025 GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes | Fully Migrated | 100
4C Solution - P4C | Italy | YES | 1 | Awaiting confirmation from Team | TBD | TBD | Yes | Migration Pending | 0
SmartHospital | Italy | YES | 1 | Awaiting confirmation from Team | TBD | TBD | TBD | Migration Pending | 0
HYDmedia | DACH | YES | 2 | Awaiting confirmation from Team | TBD | TBD | Yes | Migration Pending | 0
ORBIS Cardio | DACH | YES | 2 | Since it's part of ORBIS, it will be handled during the ORBIS repository migration. | Partially Completed | As Needed | Yes | Migration Pending | 0
BI4H | PE&T | YES | 2 | Message from Guilia on 19th Nov'24 over TEAMS: I confirm you we don't need a Git repo for our purposes at the moment. I will plan to move what's on the local GitLab instance to a SharePoint folder in the coming months. Thanks for your support! GitHub Migration: Not Applicable GitHub Actions Integration: Not Applicable Corporate JIRA Migration: Already moved to JIRA corporate | Not Applicable | Not Applicable | Yes | Partially Migrated | 34
P4P | Italy | YES | 2 | GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: In progress - 12 packages done, for remaining packages need support from team, awaiting response from Team. Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Commencing | Yes | Mostly Migrated | 67
DC4H | Italy | YES | 2 | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: Team shows interest to continue with Techton instead of GitHub Actions Corporate JIRA Migration: Already moved to JIRA corporate | Yes |  | Yes | Mostly Migrated | 67
RISonWEB | DACH | YES | 2 | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes | Fully Migrated | 100
TIP Hce | PE&T | YES | 2 | GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Team shows interest to continue with Azure DevOps instead of JIRA | Yes | Yes |  | Partially Migrated | 66
Lorenzo | PE&T | YES | 2 | GitHub Migration: In progress GitHub Actions Integration: Integration will occur as needed since it is optional. Corporate JIRA Migration: In progess | TBD | TBD | TBD | Migration Pending | 0
Rostering (AIDA) | PE&T | YES | 2 | Frans: to be aligned with Dedalus Care/HCIS GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: Team shows interest to continue with Jenkins instead of GitHub Actions Corporate JIRA Migration: Already moved to JIRA corporate | Yes |  | Yes | Mostly Migrated | 67
x-HIS | PE&T | YES | 2 | Awaiting confirmation from Team | TBD | TBD | TBD | Migration Pending | 0
MedChart | UKI/ANZ | YES | 2 | Awaiting confirmation from Team | TBD | TBD | TBD | Migration Pending | 0
Viaduct | PE&T | YES | 2 | GitHub Migration: The code repository is moved to GitHub. GitHub Actions Integration: In progress Corporate JIRA Migration: In progress | Yes | Commencing | Commencing | Migration Pending | 0
webPAS | UKI/ANZ | YES | 2 | GitHub Migration: In progress GitHub Actions Integration: Integration will occur as needed since it is optional. Corporate JIRA Migration: In progress | TBD | TBD | TBD | Migration Pending | 0
PACSonWEB | DACH | YES | 2 | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated, but yet to deploy on dev env. Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes | Fully Migrated | 100
OPUS::L | DACH | YES | 3 | Awaiting confirmation from Team | TBD | TBD | Yes | Migration Pending | 0
T4C | PE&T | YES | 3 | GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: In progress Corporate JIRA Migration: Already moved to JIRA corporate | Yes |  | Yes | Mostly Migrated | 67
amPHI | North | YES | 3 | Awaiting confirmation from Team | Not Applicable | Not Applicable | Not Applicable | Migration Pending | 0
Dedalus LIMS | UKI/ANZ | YES | 3 | Awaiting confirmation from Team | TBD | TBD | TBD | Migration Pending | 0
SwiftQueue | UKI/ANZ | YES | 3 | Awaiting confirmation from Team | TBD | TBD | TBD | Migration Pending | 0
Hexagone | France | YES | 3 | Awaiting confirmation from Team | TBD | TBD | Yes | Migration Pending | 0
Dosing | PE&T | YES | 3 | Awaiting confirmation from Team | On Hold | On Hold | On Hold | Migration Pending | 0
DxCare | PE&T | YES | 3 | Awaiting confirmation from Team | On Hold | TBD | TBD | Migration Pending | 0
ix.serv | DACH | YES | 3 | Awaiting confirmation from Team | TBD | TBD | Yes | Migration Pending | 0
i.PM (APAC) | UKI/ANZ | YES | 3 | Awaiting confirmation from Team | TBD | TBD | TBD | Migration Pending | 0
Care-Bridge | PE&T | YES | 3 | Fully aligned with Tooling Landscape program's objective, confirmed by Thomas Bender on 24-Feb-25 GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes | Fully Migrated | 100
ClinicalAide | PE&T | YES | 3 | Fully aligned with Tooling Landscape program's objective, confirmed by @Selva on 11-Mar-2025 GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes | Fully Migrated | 100
UltraGenda | North | NO-P |  | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes | Fully Migrated | 100
OneED | UKI/ANZ | NO-P |  | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Yet to start | Yes | Yes | TBD | Partially Migrated | 66
OneResponse | UKI/ANZ | NO-P |  | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Yet to start | Yes | Yes | TBD | Partially Migrated | 66
ER4H | Italy | YES |  | Awaiting confirmation from Team | TBD | TBD | Yes | Migration Pending | 0
R4C(InVitro AIS Web Reporting) | Italy | YES |  | GitHub Migration: In progress GitHub Actions Integration: Integration will occur as needed since it is optional. Corporate JIRA Migration: Already moved to JIRA corporate | TBD | TBD | TBD | Partially Migrated | 34
InVitro AIS Core (Athena) | Italy | YES |  | GitHub Migration: In progress GitHub Actions Integration: Integration will occur as needed since it is optional. Corporate JIRA Migration: Already moved to JIRA corporate | TBD | TBD | Yes | Partially Migrated | 34
Halia | Italy | Yes |  | Awaiting confirmation from Team | TBD | TBD | Yes | Migration Pending | 0
S4P | Italy | YES |  | GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: In progress Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Commencing | Yes | Mostly Migrated | 67
Labka | South | NO-P |  | GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: In progress Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Commencing | Yes | Mostly Migrated | 67
WHR | Italy | Yes |  | Awaiting confirmation from Team | TBD | TBD | TBD | Migration Pending | 0
Clinical Knowledge Portal | Italy | YES |  | GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: In progress Corporate JIRA Migration: Yet to start | Yes | Commencing | TBD | Partially Migrated | 33
MedView D | Italy | YES |  | Awaiting confirmation from Team | TBD | TBD | TBD | Migration Pending | 0
PatientAide | UKI/ANZ | NO-P |  | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Yet to start | Yes | Yes | TBD | Partially Migrated | 66

## Cost Saving
Products | Migration from | Cost per month | Total Users | Cost Saving | Annual Savings | Savings per User
RISonWeb & PACSonWeb | GitLab |  |  |  |  | 228
RISonWeb & PACSonWeb | Sonar Cloud |  |  |  |  | 360
Ultragenda | Plastic SCM |  |  |  |  | 228
Ultragenda | Team City |  |  |  |  | 240
LABKA | Perforce |  |  |  |  | 396
OneED, OneResponse, Patient Aide | Private GitHub |  |  |  |  | 432
35496
DC4H | Techton |  |  |  |  | 252
Viaduct | Azure DevOps |  |  |  |  | 0
C4H, Garsia, P4P & S4P | SVN, Gogs, Bitbucket & Jenkins |  |  |  |  | 0
|  | 0 | 1 | 0 | 0 | 0
| Note : Estimated Savings are based on Online Source data and it may change. Pending DC4H team confirmation; highlighted in yellow. | 0 | 1 | 0 | 0 | 0

## Executive Summary
KEY PERFORMANCE INDICATORS
Total Tools in Portfolio | 56
Fully Migrated Tools | 8 | 14.3%
Migration Progress | 35.2%
Annual Cost Savings | $1,087,776
Users Impacted | 275
MIGRATION STATUS BREAKDOWN
Migration Pending | 27 | 48.2%
Partially Migrated | 11 | 19.6%
Mostly Migrated | 10 | 17.9%
Fully Migrated | 8 | 14.3%
COST ANALYSIS BY SOURCE
Azure DevOps → GitHub | $0
GitLab → GitHub | $49,248
Note : Estimated Savings are based on Online Source data and it may change. Pending DC4H team confirmation; highlighted in yellow. → GitHub | $0
Perforce → GitHub | $99,792
Plastic SCM → GitHub | $46,512
Private GitHub → GitHub | $103,680
SVN, Gogs, Bitbucket & Jenkins → GitHub | $0
Sonar Cloud → GitHub | $77,760
Team City → GitHub | $48,960
Techton → GitHub | $235,872
DYNAMIC CALCULATIONS
Average Savings per Tool | 0
ROI Percentage | 388.4914 | %
Payback Months | 3.0889 | months

## Data Validation
VALIDATION RULES
Field | Valid Values | Example
Priority | High, Medium, Low | High
Strategic | Yes, No | Yes
GitHub Migration | Yes, No, Commencing, As Needed, Not Applicable | Yes
GitHub Actions | Yes, No, In Progress, As Needed, Not Applicable | In Progress
JIRA Migration | Yes, No, In Progress, Not Applicable | Yes
COST CALCULATION FORMULAS
Annual Savings | Monthly Cost Saving × 12
Savings per User | Monthly Cost Saving ÷ Total Users
ROI % | Annual Savings ÷ Migration Cost × 100
DATA SOURCES
GitHub Migration Status | GitHub Enterprise Admin Console
Cost Data | Vendor Invoices & License Agreements
User Counts | Identity Management System
Migration Costs | Project Budget & Resource Planning