## Status
Product Name/ Inventory | Regional Owner | Strategic | Priority | Comments/Status | GitHub Migration | GitHub Actions | JIRA Migration
C4H | Italy | YES | 1 | GitHub Migration: The code repository is migrated and deployed successfully. GitHub Actions Integration: The build pipeline is being transitioned to GitHub Actions, since it is an optional activity, the team chose not to deploy it on the dev environment. As of July 29, 2025, they have shown interest in adopting GitHub Actions, and an analysis is in progress Corporate JIRA Migration: Migration to corporate JIRA is completed. | Yes | Not Applicable | Yes
Clinalytix | PE&T | YES | 1 | GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: In progress by Dev. Team Corporate JIRA Migration: In porgress, planned timeline is yet to finalized | Yes | Commencing | Commencing
Orbis | PE&T | YES | 1 | GitHub Migration: The code repositories previously hosted on Bitbucket and GitLab have been successfully migrated to GitHub by product team. Migration of rest repositories, such as SVN and others, has not yet commenced. GitHub Actions Integration: Integration will occur as needed since it is optional. Corporate JIRA Migration: Already moved to JIRA corporate | Partially Completed | As Needed | Yes
GARSIA | Italy | YES | 1 | GitHub Migration: The code repository is migrated and deployed successfully. GitHub Actions Integration: The build pipeline is being transitioned to GitHub Actions, since it is an optional activity, the team chose not to deploy it on the dev environment. Corporate JIRA Migration: Migration to corporate JIRA is completed. | Yes | Not Applicable | Yes
ORBIS U/ORBIS U RIS | PE&T | YES | 1 | Since it's part of ORBIS, it will be handled during the ORBIS repository migration. | Partially Completed | As Needed | Yes
Info4U | PE&T | YES | 1 | Since it's part of ORBIS, it will be handled during the ORBIS repository migration. | Partially Completed | As Needed | Yes
Patient XCare Suite | PE&T | YES | 1 | Fully aligned with Tooling Landscape program's objective, confirmed by Stefan Grossmann on 13-Feb-2025 GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes
ORBIS ERP | PE&T | YES | 1 | Since it's part of ORBIS, it will be handled during the ORBIS repository migration. | Partially Completed | As Needed | Yes
DeepUnity | DACH | YES | 1 | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes
Dedalus Care PAS EMR | PE&T | YES | 1 | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: Team shows interest to continue with Jenkins instead of GitHub Actions Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Not Applicable | Yes
HERO | Italy | YES | 1 | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: Team shows interest to continue with Jenkins instead of GitHub Actions Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Not Applicable | Yes
4C Solution - C4C(aka P4C) | Italy | YES | 1 | Awaiting confirmation from Team | TBD | TBD | Yes
In Vitro LIS | Italy | YES | 1 | Mikhaël Sayegh will update after a workshop planned on beginning of July | TBD | TBD | Yes
4C Solution - O4C | Italy | YES | 1 | GitHub Migration: In progressGitHub. GitHub Actions Integration: Integration will occur as needed since it is optional. Corporate JIRA Migration: Already moved to JIRA corporate | TBD | TBD | Yes
Global RIS | DACH | YES | 1 | Fully aligned with Tooling Landscape program's objective, confirmed by Michaela Lehner on 30th Apr 2025 GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes
4C Solution - P4C | Italy | YES | 1 | Awaiting confirmation from Team | TBD | TBD | Yes
SmartHospital | Italy | YES | 1 | Awaiting confirmation from Team | TBD | TBD | TBD
HYDmedia | DACH | YES | 2 | Awaiting confirmation from Team | TBD | TBD | Yes
ORBIS Cardio | DACH | YES | 2 | Since it's part of ORBIS, it will be handled during the ORBIS repository migration. | Partially Completed | As Needed | Yes
BI4H | PE&T | YES | 2 | Message from Guilia on 19th Nov'24 over TEAMS: I confirm you we don't need a Git repo for our purposes at the moment. I will plan to move what's on the local GitLab instance to a SharePoint folder in the coming months. Thanks for your support! GitHub Migration: Not Applicable GitHub Actions Integration: Not Applicable Corporate JIRA Migration: Already moved to JIRA corporate | Not Applicable | Not Applicable | Yes
P4P | Italy | YES | 2 | GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: In progress - 12 packages done, for remaining packages need support from team, awaiting response from Team. Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Commencing | Yes
DC4H | Italy | YES | 2 | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: Team shows interest to continue with Techton instead of GitHub Actions Corporate JIRA Migration: Already moved to JIRA corporate | Yes | NA | Yes
RISonWEB | DACH | YES | 2 | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes
TIP Hce | PE&T | YES | 2 | GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Team shows interest to continue with Azure DevOps instead of JIRA | Yes | Yes | NA
Lorenzo | PE&T | YES | 2 | GitHub Migration: In progress GitHub Actions Integration: Integration will occur as needed since it is optional. Corporate JIRA Migration: In progess | TBD | TBD | TBD
Rostering (AIDA) | PE&T | YES | 2 | Frans: to be aligned with Dedalus Care/HCIS GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: Team shows interest to continue with Jenkins instead of GitHub Actions Corporate JIRA Migration: Already moved to JIRA corporate | Yes | NA | Yes
x-HIS | PE&T | YES | 2 | Awaiting confirmation from Team | TBD | TBD | TBD
MedChart | UKI/ANZ | YES | 2 | Awaiting confirmation from Team | TBD | TBD | TBD
Viaduct | PE&T | YES | 2 | GitHub Migration: The code repository is moved to GitHub. GitHub Actions Integration: In progress Corporate JIRA Migration: In progress | Yes | Commencing | Commencing
webPAS | UKI/ANZ | YES | 2 | GitHub Migration: In progress GitHub Actions Integration: Integration will occur as needed since it is optional. Corporate JIRA Migration: In progress | TBD | TBD | TBD
PACSonWEB | DACH | YES | 2 | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated, but yet to deploy on dev env. Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes
OPUS::L | DACH | YES | 3 | Awaiting confirmation from Team | TBD | TBD | Yes
T4C | PE&T | YES | 3 | GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: In progress Corporate JIRA Migration: Already moved to JIRA corporate | Yes | NA | Yes
amPHI | North | YES | 3 | Awaiting confirmation from Team | Not Applicable | Not Applicable | Not Applicable
Dedalus LIMS | UKI/ANZ | YES | 3 | Awaiting confirmation from Team | TBD | TBD | TBD
SwiftQueue | UKI/ANZ | YES | 3 | Awaiting confirmation from Team | TBD | TBD | TBD
Hexagone | France | YES | 3 | Awaiting confirmation from Team | TBD | TBD | Yes
Dosing | PE&T | YES | 3 | Awaiting confirmation from Team | On Hold | On Hold | On Hold
DxCare | PE&T | YES | 3 | Awaiting confirmation from Team | On Hold | TBD | TBD
ix.serv | DACH | YES | 3 | Awaiting confirmation from Team | TBD | TBD | Yes
i.PM (APAC) | UKI/ANZ | YES | 3 | Awaiting confirmation from Team | TBD | TBD | TBD
Care-Bridge | PE&T | YES | 3 | Fully aligned with Tooling Landscape program's objective, confirmed by Thomas Bender on 24-Feb-25 GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes
ClinicalAide | PE&T | YES | 3 | Fully aligned with Tooling Landscape program's objective, confirmed by @Selva on 11-Mar-2025 GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes
UltraGenda | North | NO-P |  | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Yes | Yes
OneED | UKI/ANZ | NO-P |  | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Yet to start | Yes | Yes | TBD
OneResponse | UKI/ANZ | NO-P |  | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Yet to start | Yes | Yes | TBD
ER4H | Italy | YES |  | Awaiting confirmation from Team | TBD | TBD | Yes
R4C(InVitro AIS Web Reporting) | Italy | YES |  | GitHub Migration: In progress GitHub Actions Integration: Integration will occur as needed since it is optional. Corporate JIRA Migration: Already moved to JIRA corporate | TBD | TBD | TBD
InVitro AIS Core (Athena) | Italy | YES |  | GitHub Migration: In progress GitHub Actions Integration: Integration will occur as needed since it is optional. Corporate JIRA Migration: Already moved to JIRA corporate | TBD | TBD | Yes
Halia | Italy | Yes |  | Awaiting confirmation from Team | TBD | TBD | Yes
S4P | Italy | YES |  | GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: In progress Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Commencing | Yes
Labka | South | NO-P |  | GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: In progress Corporate JIRA Migration: Already moved to JIRA corporate | Yes | Commencing | Yes
WHR | Italy | Yes |  | Awaiting confirmation from Team | TBD | TBD | TBD
Clinical Knowledge Portal | Italy | YES |  | GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: In progress Corporate JIRA Migration: Yet to start | Yes | Commencing | TBD
MedView D | Italy | YES |  | Awaiting confirmation from Team | TBD | TBD | TBD
PatientAide | UKI/ANZ | NO-P |  | Fully aligned with Tooling Landscape program's objective GitHub Migration: The code repository is already in GitHub. GitHub Actions Integration: GitHub Actions alredy integrated Corporate JIRA Migration: Yet to start | Yes | Yes | TBD
Note on G27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Team is fine with continue with Jenkins instead of GitHub Actions
Note on G34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Team is fine to continue with Jenkins instead of GitHub Actions

## Cost Saving
Products | Migration from | Cost per month | Total Users | Cost Saving
RISonWeb & PACSonWeb | GitLab | 19 | 18 | 4104
RISonWeb & PACSonWeb | Sonar Cloud | 30 | 18 | 6480
Ultragenda | Plastic SCM | 19 | 17 | 3876
Ultragenda | Team City | 20 | 17 | 4080
LABKA | Perforce | 33 | 21 | 8316
OneED, OneResponse, Patient Aide | Private GitHub | 36 | 20 | 8640
|  |  | Total | 35496
DC4H | Techton | 21 | 78 | 19656
Viaduct | Azure DevOps | MSDN license | 18
C4H, Garsia, P4P & S4P | SVN, Gogs, Bitbucket & Jenkins | Open-Source | 65
Note : Estimated Savings are based on Online Source data and it may change. Pending DC4H team confirmation; highlighted in yellow.